## Sheet1
Risk #	What is the risk?	Severity / [Pre-Mitigation] / (1-10)	Probability / [Pre-Mitigation] / (1-10)	What are you going to do about it?	When are you going to get that done?	Severity / [Post-Mitigation] / (1-10)	Probability / [Post-Mitigation] / (1-10)
1	Inclement Weather	7	1	Prepare for alternative races.	Planning	5	1
2	Shin Splints	4	8	Train legs. / Adequate stretching.	Training	4	2
3	Ankle Sprain / (During Race)	8	6	Strengthen legs. / Quality shoes.	Training	8	2
4	Ankle Sprain / (During Training)	6	3	Avoid rough terrain. Quality shoes.	Training	6	1
5	Morale Loss	6	5	Build support structure.	Planning	3	3
6	Global Pandemic	10	1	Prepare for alternative races.	Planning	5	1
7	Dislocated Shoulder	8	4	Strengthen shoulders.	Training	8	1
8	Dehydration	4	6	Hydrate during training. / Make use of drink stations during race.	Training & / Race Day	4	2