## Build
Linear Productivity Factor | 2.51
Exponential Size Penalty | 1.03
Function Point Estimation | Count | FP Factor | Function Points
Inputs | 10 | 4 | 40
Interface Files | 6 | 7 | 42
Outputs | 6 | 5 | 30
Queries | 6 | 4 | 24
Logical Tables | 4 | 10 | 40
|  | Total | 176
Language | Factor | FP | KSLOC | Engineer Months | Engineer / Month | Development Total | Ongoing Est. (Month)
C++ | 53 | 176 | 9.328 | 25.0355 | 7575 | 189643.7578 | 9482.1879
C# | 48 | 176 | 8.448 | 22.6063 | 7575 | 171243.021 | 8562.1511
Java | 46 | 176 | 8.096 | 21.6368 | 7575 | 163898.4978 | 8194.9249

## Buy
| Odoo | Reckon | Xero
Monthly Flat Cost | 0 | 67 | 67
Monthly User Cost | 128 | 0 | 7
Company Size Costs (Monthly)
50 | 6400 | 67 | 417
100 | 12800 | 67 | 767
250 | 32000 | LIMIT 200 | 1817
500 | 64000 | LIMIT 200 | 3567
Company Size Costs (Yearly)
50 | 76800 | 804 | 5004
100 | 153600 | 804 | 9204
250 | 384000 | LIMIT 200 | 21804
500 | 768000 | LIMIT 200 | 42804

## Build vs Buy
|  | Custom |  | Odoo |  | Reckon |  | Xero
Category | Factor | Score | Value | Score2 | Value3 | Score4 | Value5 | Score6 | Value7
Upfront Cost | 3 | 1 | 3 | 5 | 15 | 5 | 15 | 5 | 15
Monthly Cost | 5 | 1 | 5 | 5 | 25 | 3 | 15 | 3 | 15
User Cost | 3 | 5 | 15 | 1 | 3 | 5 | 15 | 4 | 12
Flexibility | 4 | 5 | 20 | 5 | 20 | 5 | 20 | 5 | 20
Support | 4 | 2 | 8 | 5 | 20 | 4 | 16 | 4 | 16
Breadth of Features | 5 | 3 | 15 | 4 | 20 | 4 | 20 | 4 | 20
Cost for Growth | 5 | 5 | 25 | 1 | 5 | 3 | 15 | 4 | 20
Total |  |  | 91 | Value3: 108; Value5: 116; Value7: 118

## Cost Over Time
Quarter-by-Quarter Costs
|  | Custom |  |  |  | Oodo |  |  |  | Reckon |  |  |  | Xero
Users | Month | Initial | Flat/Mo | User/Mo | Total | Initial | Flat/Mo | User/Mo | Total | Initial | Flat/Mo | User/Mo | Total | Initial | Flat/Mo | User/Mo | Total
200 | 0 | 163898.4978 | 8194.9249 | 0 | 163898.4978 | 0 | 0 | 128 | 0 | 0 | 67 | 0 | 0 | 0 | 67 | 7 | 0
200 | 4 | 163898.4978 | 8194.9249 | 0 | 196678.1974 | 0 | 0 | 128 | 102400 | 0 | 67 | 0 | 268 | 0 | 67 | 7 | 5868
200 | 8 | 163898.4978 | 8194.9249 | 0 | 229457.8969 | 0 | 0 | 128 | 204800 | 0 | 67 | 0 | 536 | 0 | 67 | 7 | 11736
200 | 12 | 163898.4978 | 8194.9249 | 0 | 262237.5965 | 0 | 0 | 128 | 307200 | 0 | 67 | 0 | 804 | 0 | 67 | 7 | 17604
200 | 16 | 163898.4978 | 8194.9249 | 0 | 295017.2961 | 0 | 0 | 128 | 409600 | 0 | 67 | 0 | 1072 | 0 | 67 | 7 | 23472
200 | 20 | 163898.4978 | 8194.9249 | 0 | 327796.9956 | 0 | 0 | 128 | 512000 | 0 | 67 | 0 | 1340 | 0 | 67 | 7 | 29340
200 | 24 | 163898.4978 | 8194.9249 | 0 | 360576.6952 | 0 | 0 | 128 | 614400 | 0 | 67 | 0 | 1608 | 0 | 67 | 7 | 35208
200 | 28 | 163898.4978 | 8194.9249 | 0 | 393356.3948 | 0 | 0 | 128 | 716800 | 0 | 67 | 0 | 1876 | 0 | 67 | 7 | 41076
200 | 32 | 163898.4978 | 8194.9249 | 0 | 426136.0943 | 0 | 0 | 128 | 819200 | 0 | 67 | 0 | 2144 | 0 | 67 | 7 | 46944
200 | 36 | 163898.4978 | 8194.9249 | 0 | 458915.7939 | 0 | 0 | 128 | 921600 | 0 | 67 | 0 | 2412 | 0 | 67 | 7 | 52812
200 | 40 | 163898.4978 | 8194.9249 | 0 | 491695.4934 | 0 | 0 | 128 | 1024000 | 0 | 67 | 0 | 2680 | 0 | 67 | 7 | 58680
200 | 44 | 163898.4978 | 8194.9249 | 0 | 524475.193 | 0 | 0 | 128 | 1126400 | 0 | 67 | 0 | 2948 | 0 | 67 | 7 | 64548
200 | 48 | 163898.4978 | 8194.9249 | 0 | 557254.8926 | 0 | 0 | 128 | 1228800 | 0 | 67 | 0 | 3216 | 0 | 67 | 7 | 70416
200 | 52 | 163898.4978 | 8194.9249 | 0 | 590034.5921 | 0 | 0 | 128 | 1331200 | 0 | 67 | 0 | 3484 | 0 | 67 | 7 | 76284
200 | 56 | 163898.4978 | 8194.9249 | 0 | 622814.2917 | 0 | 0 | 128 | 1433600 | 0 | 67 | 0 | 3752 | 0 | 67 | 7 | 82152
200 | 60 | 163898.4978 | 8194.9249 | 0 | 655593.9913 | 0 | 0 | 128 | 1536000 | 0 | 67 | 0 | 4020 | 0 | 67 | 7 | 88020
200 | 64 | 163898.4978 | 8194.9249 | 0 | 688373.6908 | 0 | 0 | 128 | 1638400 | 0 | 67 | 0 | 4288 | 0 | 67 | 7 | 93888
200 | 68 | 163898.4978 | 8194.9249 | 0 | 721153.3904 | 0 | 0 | 128 | 1740800 | 0 | 67 | 0 | 4556 | 0 | 67 | 7 | 99756
200 | 72 | 163898.4978 | 8194.9249 | 0 | 753933.09 | 0 | 0 | 128 | 1843200 | 0 | 67 | 0 | 4824 | 0 | 67 | 7 | 105624
200 | 76 | 163898.4978 | 8194.9249 | 0 | 786712.7895 | 0 | 0 | 128 | 1945600 | 0 | 67 | 0 | 5092 | 0 | 67 | 7 | 111492
200 | 80 | 163898.4978 | 8194.9249 | 0 | 819492.4891 | 0 | 0 | 128 | 2048000 | 0 | 67 | 0 | 5360 | 0 | 67 | 7 | 117360
200 | 84 | 163898.4978 | 8194.9249 | 0 | 852272.1886 | 0 | 0 | 128 | 2150400 | 0 | 67 | 0 | 5628 | 0 | 67 | 7 | 123228
200 | 88 | 163898.4978 | 8194.9249 | 0 | 885051.8882 | 0 | 0 | 128 | 2252800 | 0 | 67 | 0 | 5896 | 0 | 67 | 7 | 129096
200 | 92 | 163898.4978 | 8194.9249 | 0 | 917831.5878 | 0 | 0 | 128 | 2355200 | 0 | 67 | 0 | 6164 | 0 | 67 | 7 | 134964
200 | 96 | 163898.4978 | 8194.9249 | 0 | 950611.2873 | 0 | 0 | 128 | 2457600 | 0 | 67 | 0 | 6432 | 0 | 67 | 7 | 140832
200 | 100 | 163898.4978 | 8194.9249 | 0 | 983390.9869 | 0 | 0 | 128 | 2560000 | 0 | 67 | 0 | 6700 | 0 | 67 | 7 | 146700
200 | 104 | 163898.4978 | 8194.9249 | 0 | 1016170.6865 | 0 | 0 | 128 | 2662400 | 0 | 67 | 0 | 6968 | 0 | 67 | 7 | 152568
200 | 108 | 163898.4978 | 8194.9249 | 0 | 1048950.386 | 0 | 0 | 128 | 2764800 | 0 | 67 | 0 | 7236 | 0 | 67 | 7 | 158436
200 | 112 | 163898.4978 | 8194.9249 | 0 | 1081730.0856 | 0 | 0 | 128 | 2867200 | 0 | 67 | 0 | 7504 | 0 | 67 | 7 | 164304